## Slide 1: IEFT Event @ Hilton Atlanta (ATLAH)
November 2, 2012 – November 9, 2012

## Slide 2: I. Remove StayConnected Presence

## Slide 3: Process to Remove ATT Gateway and StayConnected Presence
Greg Purcell
Sr. Prod Marketing Manager - AWSc
Joe Roberts
Sales Center VP
AT&T Business Sales
Jim Jeffcoat
AVP Service Management
Peter Feldman
AVP Engineering
Wi-Fi Solutions
Adam Brzyski
Network Integration Engagement Manager
Phil Hartfield
WiFi Sales Director
Glenn Wolonsky General Manager
Tim Thompson
Director
Strategic Client Group
Kendal Showalter
Area Manager Service Mgmt AWS
Bobby Stroud
Network Integration Engagement Manager
Alania Cater
Area Mgr – Venue Deployment AWS
Micah McDonald
Area Mgr – Venue Deployment AWS
Andrew Bouseman
AVP Network Services
Wi-Fi Solutions
Dennis Whiteside
AVP Mktg & Tech Sales
Wi-Fi Solutions
Kevin Hansel
Executive Director
Information Technology
Wi-Fi Solutions
Dee Nesbitt
Senior PM -NPM
Step | Process | Owner | Time Interval
1 | ATT Senior Network Engineer (SNE) to provide VLANs to IETF for their router to communicate with the APs. | ATT SNE | Prior to 11/2
2 | Designated Hotel Staff to remove all StayConnected Collateral from the Guest Rooms, Meeting Rooms, Public Area, etc. | Hotel | No later than 11/2
3 | All participants to join the ATT Conference Bridge provided to begin the cutover process. This bridge will remain open for the duration of the change process. (Dial in #: 888-675-2546 Conference Room #: 8109046) | All Participants | 11/2 @ 8am CST
3a | ATT SNE to reconfigure all Access Points (APs) to remove the ATT & Hhonors SSID’s and broadcast the “Free” SSID throughout the Hotel. | ATT SNE | 3 – 4 Hours
3b | ATT SNE to work with the Hotels IT Manager - James Caldwell (Hotel IT) to verify AP changes. James to walk a few floors and verify which SSID’s are broadcasting. | ATT SNE/ Hotel IT | 1 hour
3c | IETF / Hotel IT to work remotely with ATT SNE to swing cable from the NMD to IETF’s router. Test and verify. | IETF/ Hotel IT/ ATT SNE | 30 Minutes
4 | Gateway is removed. Front Desk at the property will now be responsible to take all the guest room maintenance and support calls and not ATT NOC. The Front Desk will have the responsibility to call the IETF group directly for support as AT&T NOC/Engineers will have no involvement since gateway does not exist. | Hotel / IETF | 8 Days

## Slide 4: II. Reestablish StayConnected Presence

## Slide 5: Process to Reestablish ATT Gateway & StayConnected Presence
Joe Roberts
Sales Center VP
AT&T Business Sales
Jim Jeffcoat
AVP Service Management
Peter Feldman
AVP Engineering
Wi-Fi Solutions
Adam Brzyski
Network Integration Engagement Manager
Phil Hartfield
WiFi Sales Director
Glenn Wolonsky General Manager
Tim Thompson
Director
Strategic Client Group
Kendal Showalter
Area Manager Service Mgmt AWS
Bobby Stroud
Network Integration Engagement Manager
Alania Cater
Area Mgr – Venue Deployment AWS
Micah McDonald
Area Mgr – Venue Deployment AWS
Andrew Bouseman
AVP Network Services
Wi-Fi Solutions
Dennis Whiteside
AVP Mktg & Tech Sales
Wi-Fi Solutions
Kevin Hansel
Executive Director
Information Technology
Wi-Fi Solutions
Dee Nesbitt
Senior PM -NPM
Step | Process | Owner | Time Interval
1 | ATT Project Manager - Debby Guida (PM) to dispatch ATT Field Services (FS) to work with our SNE Remotely to reestablish StayConnected Presence at ATLAH. ATT FS to arrive onsite 11/9 @ 8am CST to begin the cutover process | ATT PM / ATT FS | 11/9 @ 8am CST
2 | All participants to join the ATT Conference Bridge provided to begin the cutover process. This bridge will remain open for the duration of the change process. (Dial in #: 888-675-2546 Conference Room #: 8109046) | All Participants | 11/9 @ 8am CST
2a | ATT FS to work with IETF as well as the SNE Remotely to swing cable from IETF’s router to the NMD. | ATT FS / IETF / ATT SNE | 30 Minutes
2b | ATT SNE to work with ATT FS to remove the “Free” SSID and implement the ATT & Hhonors SSID’s. | ATT SNE/ ATT FS | 3 – 4 Hours
2c | ATT FS to complete network verification process to ensure all equipment is functioning as it was prior to removing the Gateway. | ATT FS | 2 hours
3 | Designated Hotel Staff to place StayConnected Collateral back into the Guest Rooms. | Hotel | Once Cut is Complete

## Slide 6: III. ATT Contact & Escalation Process Matrix

## Slide 7: ATT Contact & Escalation Process Matrix
Joe Roberts
Sales Center VP
AT&T Business Sales
Jim Jeffcoat
AVP Service Management
Peter Feldman
AVP Engineering
Wi-Fi Solutions
Adam Brzyski
Network Integration Engagement Manager
Phil Hartfield
WiFi Sales Director
Glenn Wolonsky General Manager
Tim Thompson
Director
Strategic Client Group
Kendal Showalter
Area Manager Service Mgmt AWS
Bobby Stroud
Network Integration Engagement Manager
Alania Cater
Area Mgr – Venue Deployment AWS
Micah McDonald
Area Mgr – Venue Deployment AWS
Andrew Bouseman
AVP Network Services
Wi-Fi Solutions
ATT Contact | Title / Position | Abbr. | Phone #
Kelly Foster | ATT Service Executive | ATT SE | 512.568.4608
Debby Guida | ATT Project Manager | ATT PM | 512.519.6743
Lucien Gaudet | ATT Senior Network Engineer | ATT SNE | 512.568.4608
ATT Bat Phone | ATT NOC (TTL) Technical Team Lead On Duty **Used ONLY if break-fix process is required** | ATT NOC | 512.438.8231
ATT Conference Bridge Number: Dial in #: 888-675-2546 Conference Room #: 8109046#
11/2 @8am
11/9 @8am